## Project and Estimation Summary
Testing Project - Estimation
Project Information |  |  |  | 0%
Project/ Release ID: | NGSS | Test Project Manager: | Vipin Nambiar, Test Manager | 25%
Project/ Release Name: | NGSS | Application Name: | NGSS | 50%
75%
Estimation Summary |  |  |  | 100%
Estimator(s): | Ravikanth Mirsappalli | Reviewer(s): | Vipin Nambiar, Test Manager
Estimate Version: | 1 | Date of Estimation: | 22/8/2019
|  | Total Estimate Based on WBS: | 145.5
Requirement clarity%: | 100% | Contingency for lack of requirement clarity: | 0
No of lead days provided for ROM estimate: | 1 | Contingency for turn around time: | 0
Contingency%: | 0% | Contingency for known and unknown risks: | 0
Test Management%: | 0 | Test Management Effort | 0
Onsite coordination%: | 0% | Onsite Coordination Effort: | 0
|  | Total Estimated Hours (including Contingency, Test Management and Onsite coordination): | 145.5
|  | Total number of Test Scripts | 21

## Meta Data
Testing Project - Estimation
Test Script Classification
Attributes | Simple | Medium | High | Very High
Number of transactions Involved | < 5 | 6 to 10 | 20 to 30 | > 30
Number of Parameterization | 1 to 5 | 6 to 10 | 10 to 20 | >30
Number of Correlation | 1 to 5 | 6 to 10 | 10 to 20 | >30
System Dependency | None | Middleware or batch process | External applications | Third party systems and Mandatory pre-requisites
Criticality and complexity of the functionality | Low | Medium | Complex | Complex and Critical
Environment complexity | Low | Medium | High | Complex
Test Data Availability and Validation | Easily obtained or modified | Complex Test data setup with extra effort | Test data is dependent on upstream or downstream systems | Test data is prepared by support tools to generate and database to store and manage
Productivity Data for Application: | Service Renewal
Web Protocol | 3 | 5 | 7 | 10
Web service/REST | 0.5 | 0.75 | 1.5 | 2
Ajax True Client | 4 | 6 | 8 | 10
Ajax True Client Maint | 1 | 1 | 3 | 5
Guidelines for Test Script Classification table
All 15 parameters are not applicable for all Applications or Test Scripts
Values in C13 through F13 are used for calculating the Test Case creation effort for each requirement in TC Estimates tab

## Estimation Breakdown
Phase | Effort in hours
Requirements Analysis | 8
Test Estimation and Planning | 8
Test data Preparation | 1
Test Design | 84.5
Test Execution | 0
Test Execution in Stage or Prod Fix Environment | 36
Regression Test Identification and Update | 0
Regression Test Execution Manual | 0
Regression Test Execution Automation | 0
Defect Management | 0
Test data support for UAT, upstream and downstream applications | 0
UAT Support | 0
Production checkout support | 0
Post Go-Live Support | 0
Communication and Coordination and documentation | 8
Closure | 0
Adjustments | 0
Total Estimate | 145.5

## TS Estimates
Testing Project - Estimation
Test Script Design | [5 empty] | Test Case Design and Execution Effort Summary
Requirement | Simple TCs | Average TCs | High TCs | Very High TCs | TS Design Hours | Total Test Script Design: | 84.5
Web service/REST | 21 | 0 | 0 | 0 | 84.5 | Total Test Script Review: | 8.45
[5 empty] | 0 | Total Test Script Rework: | 0
[5 empty] | 0 | Number of Test Cycles Planned: | 6
[5 empty] | 0 | Test Script Execution: | 36
[5 empty] | 0 | Test Execution Failure Rate: | 0%
[5 empty] | 0 | Total Test Re-execution: | 0
0
Total Estimated Test Script (By Complexity): | 21 | 0 | 0 | 0 | 84.5
Estimated Test cases - Grand Total: | 21 |  |  | Total:
Test Execution
Test Types | Execution Duration | Scenario Design | Report Preparation | TS Identification/ Update/Execution Hours
Dry Run | 1 | 0.5 | 0.5 | 2
Load Test | 2 | 1 | 1 | 4
Total Estimated Test Executions | 6 | 1.5 | 1.5 | 6
Total: | 6

## Assumptions
Testing Project - Estimation
Serial # | Assumptions, Constraints and Dependencies
1 | Estimation is based on a the intial discussion wiht NGSS team, 21 API's are in scope now assuming few more API's could be in scope
2 | Load Model will be 10 k hits /hour intially and for the new scenario load will be decided
3 | Execution will be done along with the dev teams initially.
4 | The Stage environment will be used for scripting. All the scripts will be validated in LnP instance.
5 | The functional help will be provided to L&P team

## In Scope
Testing Project - Estimation
Serial # | In Testing Scope for the Application Release or Project
1 | Estimation is based on a the intial discussion wiht NGSS team, 21 API's are in scope now , scripting is progress .. Types of tests would be added after discussing with the project team
2 | load model is finalised according to the API
3 | Execution will be done along with the dev teams, detailed plan is yet to be finalised
4 | The Stage environment will be used for scripting. All the scripts will be validated in LnP instance.
5 | The functional help will be provided to L&P team

## Out of Scope
Testing Project - Estimation
Sl No | Out of Testing Scope for the Application Release or Project
1 | No other transactions apart from those listed in the test plan team will be out of scope for this project
2 | Any additional features for L&P might required re-estimation

## Template Revision History
Testing Project - Estimation
Template Revision History
Author: | Christobel S
Version Number | Release Date | Description of Change/s made | Reviewed by (Name & Role) | Approved by (Name & Role)
1 | 2016-07-28 | Version created for NetApp | Bijan S, Joseph Xavier and Mark | Mark laws- IT Manager, Test Services
1.1 | 2017-01-12 | Updated to auto calculate and populate the estimates for various phases with minimum details to be keyed in during estimation. This if to make it easier for Test teams to use the estimation tool and process and also guide on the likely estimates for various Testing phases | Dins and Rajeev
1.2 | 2017-01-17 | Incorporated comments from Dins | Dins and Rajeev
1.3 | 2017-01-17 | Incorporated comments from Mark | Dins and Rajeev
1.4 | 2017-01-26 | Updated date format in template revision history and template guidelines | Dins and Rajeev
1.5 | 2017-05-09 | Updated with lessons learnt in previous releases and added sections for In scope and out of scope | Dins and Rajeev
1.6 | 2017-07-26 | Incorporated feedback from Test managers and NetApp leads after a brainstorming session | Dins and Rajeev
1.7 | 2017-08-28 | Updated the following feedback: 1. Common metadata for all applications 2. improved test case complexity categorization 3. improved effort split for clarity | Dins and Rajeev
2 | 2017-09-20 | Incorporated feedback from Test managers and NetApp leads after a brainstorming session | Dins and Rajeev
2.1 | 2017-12-18 | Provided provision for entering requirements clarity % to calculate contingency | Rajeev
2.1 | 2017-12-21 | Incorporated review comments from Rajeev | Rajeev
2.2 | 2018-01-08 | Incorporated review comments from Dins and Rajeev on test management effort | Dins and Rajeev